## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 |  |  | Application failed to start — missing Maven dependencies for Jersey. | Sprint1 |  |  | Added required dependencies (jersey-server, jersey-container-servlet) in pom.xml. | 2025-09-11 | Closed | Backend running successfully.
2 |  |  | Unable to connect to MySQL — JDBC URL misconfigured in properties file. | Sprint1 |  |  | Corrected MySQL connection string and verified DB creation through DAO. | 2025-09-16 | Closed | Database connected successfully.
3 |  |  | Transaction API allowed money transfer even when sender had insufficient balance. | Sprint2 |  |  | Added validation for balance check before transaction. | 2025-09-25 | Closed | Tested and verified validation message.
4 |  |  | Account creation API allowed duplicate account numbers. | Sprint2 |  |  | Added unique constraint in MySQL and validation in service layer. | 2025-09-27 | Closed | Duplicate creation prevented.
5 |  |  | Money transfer API only deducted amount from sender, receiver’s balance not updated. | Sprint2 |  |  | Fixed logic to update both sender and receiver balances. | 2025-09-30 | Closed | Transfer verified successfully.
6 |  |  | Email notifications feature not sending emails from admin module. | Sprint 3 |  |  | Corrected SMTP configuration and credentials in .env. | 2025-10-10 | Closed | Email sending confirmed.
7 |  |  | Excel download feature exported an empty sheet despite available transactions. | Sprint 3 |  |  | Fixed data export mapping and verified output file. | 2025-10-12 | Closed | Excel file downloads correctly.
8 |  |  | User signup did not redirect automatically to dashboard after registration. | Sprint 4 |  |  | Updated signup response handling and navigation logic. | 2025-10-23 | Closed | Redirection works properly.
9 |  |  | Dashboard overview cards showing “0” instead of live counts. | Sprint 4 |  |  | Linked dashboard with backend /getAll API endpoints. | 2025-10-26 | Closed | Dashboard displays live data.
10 |  |  | Admin login always returned “Invalid credentials” even for valid users. | Sprint 4 |  |  | Corrected JSON request key names (username, password) in controller. | 2025-10-28 | Closed | Admin login successful.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others