## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint1 | Sprint1 |  | As a System Admin, I want a Customer table to store user details (Name, Email, Phone, Aadhaar, customer_pin, aadhar_number, Date of birth). |  |  |  | 3- Completed
Sprint1 | Sprint1 |  | As a System Admin, I want an Account table to store bank account details (Balance, Account Type, Account Number, Account Name, Phone number linked, ifsc code, bank name) linked to a customer. |  |  |  | 3- Completed
Sprint1 | Sprint1 |  | As a System Admin, I want a Transaction table to log all fund transfers. |  |  |  | 3- Completed
Sprint1 | Sprint1 |  | As a Developer, I want a functional REST API setup (Jersey/Tomcat) to serve endpoints. |  |  |  | 3- Completed
Sprint1 | Sprint1 |  | As a User, I want to be able to create, read, update, and delete my Customer profile via an API. |  |  |  | 3- Completed
Sprint2 | Sprint2 |  | As a User, I want to be able to create, read, update, and delete my Account details via an API. |  |  |  | 3- Completed
Sprint2 | Sprint2 |  | As a User, I want to transfer money to another account, with API checks for my PIN and available balance. |  |  |  | 3- Completed
Sprint2 | Sprint2 |  | As a User, I want to view the transaction history for my account via an API. |  |  |  | 3- Completed
Sprint2 | Sprint2 |  | As a Developer, I want unit tests (JUnit/Mockito) for all backend service layers. |  |  |  | 3- Completed
Sprint3 | Sprint3 |  | As a User, I want to receive an email notification (sender and receiver) after a successful transaction. |  |  |  | 3- Completed
Sprint3 | Sprint3 |  | As a User, I want to download my transaction history as an Excel file via an API. |  |  |  | 3- Completed
Sprint3 | Sprint3 |  | As an Admin, I want a secure API endpoint to log in to an admin portal. |  |  |  | 3- Completed
Sprint3 | Sprint3 |  | As a User, I want to submit a "Contact Us" query to the admin via an API. |  |  |  | 3- Completed
Sprint3 | Sprint3 |  | As an Admin, I want to receive an email notification when a new user query is submitted. |  |  |  | 3- Completed
Sprint3 | Sprint3 |  | As an Admin, I want to view all user-submitted queries via an API. |  |  |  | 3- Completed
Sprint4 | Sprint4 |  | As a new User, I want a web page to register (signup) for the banking service. |  |  |  | 3- Completed
Sprint4 | Sprint4 |  | As an existing User, I want a web page to log in to the application |  |  |  | 3- Completed
Sprint4 | Sprint4 |  | As a User, I want to see a dashboard with an overview of total customers, accounts, and transactions. |  |  |  | 3- Completed
Sprint4 | Sprint4 |  | As a User, I want a web interface to add, search, edit, and delete customers. |  |  |  | 3- Completed
Sprint4 | Sprint4 |  | As a User, I want a web interface to create and search for bank accounts. |  |  |  | 3- Completed
Sprint4 | Sprint4 |  | As a User, I want a web interface to make a transaction and view my transaction history. |  |  |  | 3- Completed
Sprint4 | Sprint4 |  | As an Admin, I want a web interface to log in and view all system data (customers, accounts, transactions and queries). |  |  |  | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
| 1 | As a System Admin, I want a Customer table to store user details (Name, Email, Phone, Aadhaar, customer_pin, aadhar_number, Date of birth). | 2025-09-08 | 2025-09-21 |  |  | Done
| 2 | As a System Admin, I want an Account table to store bank account details (Balance, Account Type, Account Number, Account Name, Phone number linked, ifsc code, bank name) linked to a customer. | 2025-09-08 | 2025-09-21 |  |  | Done
| 3 | As a System Admin, I want a Transaction table (Sender account, Receiver account, Amount,Description) to log all fund transfers. | 2025-09-08 | 2025-09-21 |  |  | Done
| 4 | As a Developer, I want a functional REST API setup (Jersey/Tomcat) to serve endpoints. | 2025-09-08 | 2025-09-21 |  |  | Done
| 5 | As a User, I want to be able to create, read, update, and delete my Customer profile via an API. | 2025-09-08 | 2025-09-21 |  |  | Done
SPRINT 2 BACKLOG
| 6 | As a User, I want to be able to create, read, update, and delete my Account details via an API. | 2025-09-22 | 2025-10-05 |  |  | Done
| 7 | As a User, I want to transfer money to another account, with API checks for my PIN and available balance. | 2025-09-22 | 2025-10-05 |  |  | Done
| 8 | As a User, I want to view the transaction history for my account via an API. | 2025-09-22 | 2025-10-05 |  |  | Done
| 9 | As a Developer, I want unit tests (JUnit/Mockito) for all backend service layers. | 2025-09-22 | 2025-10-05 |  |  | Done
SPRINT 3 BACKLOG
| 10 | As a User, I want to receive an email notification (sender and receiver) after a successful transaction. | 2025-10-06 | 2025-10-19 |  |  | Done
| 11 | As a User, I want to download my transaction history as an Excel file via an API. | 2025-10-06 | 2025-10-19 |  |  | Done
| 12 | As an Admin, I want a secure API endpoint to log in to an admin portal. | 2025-10-06 | 2025-10-19 |  |  | Done
| 13 | As a User, I want to submit a "Contact Us" query to the admin via an API. | 2025-10-06 | 2025-10-19 |  |  | Done
| 14 | As an Admin, I want to receive an email notification when a new user query is submitted. | 2025-10-06 | 2025-10-19 |  |  | Done
| 15 | As an Admin, I want to view all user-submitted queries via an API. | 2025-10-06 | 2025-10-19 |  |  | Done
SPRINT 4 BACKLOG
| 16 | As a new User, I want a web page to register (signup) for the banking service. | 2025-10-20 | 2025-10-28 |  |  | Done
| 17 | As an existing User, I want a web page to log in to the application. | 2025-10-20 | 2025-10-28 |  |  | Done
| 18 | As a User, I want to see a dashboard with an overview of total customers, accounts, and transactions. | 2025-10-20 | 2025-10-28 |  |  | Done
| 19 | As a User, I want a web interface to add, search, edit, and delete customers. | 2025-10-20 | 2025-10-28 |  |  | Done
| 20 | As a User, I want a web interface to create and search for bank accounts. | 2025-10-20 | 2025-10-28 |  |  | Done
| 21 | As a User, I want a web interface to make a transaction and view my transaction history. | 2025-10-20 | 2025-10-28 |  |  | Done
| 22 | As an Admin, I want a web interface to log in and view all system data (customers, accounts, transactions, queries). | 2025-10-20 | 2025-10-28 |  |  | Done
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7